|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Week 1 | 7 days | 13 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 2 | Create planning document | 4 days | 13 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 3 | Read and write down activities in Project Exam 1 | 1 day | 13 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 4 | Create plan for activities | 1 day | 14 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 5 | Functional Spec and Gantt chart | 2 days | 15 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 6 | Research | 3 days | 17 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 7 | Target audience/ research/ personae | 2 days | 17 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 8 | Look at similar websites and take notes | 4 hours | 19 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 9 | Read and look for pictures/api´s. | 4 hours | 19 Sep 2021 at 12:00 | Jan Emil Gustafsson |
| 10 | Gannt chart project schedule finished |  | 19 Sep 2021 at 20:00 |  |
| 11 | Week 2 | 5 days | 20 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 12 | Design | 5 days | 20 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 13 | Create pencil sketches | 2 days | 20 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 14 | Assemble color palette | 1 day | 22 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 15 | Layout planning | 1 day | 23 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 16 | Images (sizing) | 1 day | 24 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 17 | Weekend (time off) |  | 24 Sep 2021 at 16:00 | Jan Emil Gustafsson |
| 18 | Week 3 | 5 days | 27 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 19 | Design | 5 days | 27 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 20 | Create mockup | 4 days | 27 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 21 | Mockup mobile devices | 2 days | 27 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 22 | Mockup laptop/desktop | 2 days | 29 Sep 2021 at 08:00 | Jan Emil Gustafsson |
| 23 | Text flow | 1 day | 1 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 24 | Graphic designs and mockups finished |  | 1 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 25 | Weekend (time off) |  | 1 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 26 | Week 4 | 5 days | 4 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 27 | HTML & CSS mobile devices | 5 days | 4 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 28 | HTML layout and frame | 5 days | 4 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 29 | Weekend (time off) |  | 8 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 30 | Week 5 | 5 days | 11 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 31 | HTML & CSS mobile devices continued | 5 days | 11 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 32 | HTML layout and frame | 1 day | 11 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 33 | CSS Mobile devices | 3 days | 12 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 34 | Testing | 1 day | 15 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 35 | HTML & CSS mobile devices finished |  | 15 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 36 | Weekend (time off) |  | 15 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 37 | Week 6 | 5 days | 18 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 38 | CSS laptop/desktop devices | 5 days | 18 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 39 | Write CSS laptop/desktop devices | 3 days | 18 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 40 | Testing | 4 hours | 21 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 41 | Outside testing (family user test) | 4 hours | 21 Oct 2021 at 12:00 | Jan Emil Gustafsson |
| 42 | Implement outside testing feedback (if applicable) | 1 day | 22 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 43 | Submit website/rollout |  | 22 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 44 | Weekend (time off) |  | 22 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 45 | Week 7 | 5 days | 25 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 46 | Write report | 5 days | 25 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 47 | Compile report material | 1 day | 25 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 48 | Sources and inspiration | 1 day | 26 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 49 | Start writing report | 2 days | 27 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 50 | Submit report | 1 day | 29 Oct 2021 at 08:00 | Jan Emil Gustafsson |
| 51 | Weekend (time off) |  | 29 Oct 2021 at 16:00 | Jan Emil Gustafsson |
| 52 | Week 8 (Buffer week) | 5 days | 1 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 53 | Buffer | 5 days | 1 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 54 | Buffer | 5 days | 1 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 55 | Weekend (time off) |  | 5 Nov 2021 at 16:00 | Jan Emil Gustafsson |
| 56 | Week 9 (Buffer week) | 5 days | 8 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 57 | Buffer | 5 days | 8 Nov 2021 at 08:00 |  |
| 58 | Buffer | 5 days | 8 Nov 2021 at 08:00 |  |
| 59 | Weekend (time off) |  | 12 Nov 2021 at 16:00 | Jan Emil Gustafsson |
| 60 | Week 10 (Buffer week) | 5 days | 15 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 61 | Write and submit report? | 5 days | 15 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 62 | Finish writing report | 3 days | 15 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 63 | Quality control on report and website | 2 days | 18 Nov 2021 at 08:00 | Jan Emil Gustafsson |
| 64 | Submit report (if applicable) |  |  | Jan Emil Gustafsson |
| 65 | Weekend (time off) |  | 19 Nov 2021 at 16:00 | Jan Emil Gustafsson |